## Summary
A1 — I/O List, Audit View
Project | Kingsford Hotel Bacolod — BMS Rehabilitation (A/B run)
Canonical source | A1-io-list.yaml
How to record corrections | Edit the canonical YAML directly — add a verification: block to the affected row(s)
Totals
Total I/O points | 762
Unique equipment instances | 125
Systems represented | 4
Verification status
Status | Count | % of total
verified | 0 | 0%
needs_correction | 0 | 0%
uncertain | 0 | 0%
unverified | 762 | 100%
⚠ Known weak points
Equipment quantities are derived from the customer's points list. Cross-verify against mechanical floor plans (Q-008) and architectural plans (Q-005). Where the points list shows aggregate counts without per-tag enumeration, the gap is captured as Q-021.
How corrections flow
Edit A1-io-list.yaml — add a verification: block to any row where you confirm or correct the equipment, location, or panel assignment.
Re-run the deliverables generator to refresh downstream artifacts.

## By System
System | Equipment instances | I/O points
VENT | 62 | 366
AC | 32 | 334
HWL | 20 | 48
EE | 11 | 14
TOTAL | 125 | 762

## By Location
Location | Equipment instances
2nd Floor | 25
2nd Floor (Plant Room) | 22
3rd Floor (Guestroom) | 20
Roofdeck | 19
Ground Floor | 12
Lower Ground | 12
3rd Floor (Amenity) | 7
2nd Floor (Casino) | 5
Basement (Genset) | 2
Basement | 1

## By Panel
Panel | Equipment instances
FCP-2F | 30
FCP-3F | 27
MCP-PLANT | 22
FCP-RD | 19
FCP-BSMT | 15
FCP-GF | 12

## Verification schema
How to record verification / corrections in A1-io-list.yaml
Find the affected row in the YAML by ID (Detail sheet column A) and add a verification: block:
- id: chws.ch-1.entering-chw-temp
verification: # ADDED by team
status: needs_correction # unverified ¦ verified ¦ needs_correction ¦ uncertain
verified_by: J. Cruz
verified_date: 2026-05-10
drawing_ref: "EE-09 grid B-2"
notes: ""
After saving, re-run: python3 _playbook/tools/generate-deliverables.py <project>
Corrections propagate to B4 manhours, BOQ, and final deliverables automatically.
Recommended verification methods (priority order):
1. Site walkthrough with measurement (most accurate; for cable lengths, after structural completion).
2. Properly-scaled architectural drawings.
3. Mechanical contractor's tray layout combined with BMS panel locations.
4. A-001 default with ±20% contingency in BOQ — last resort.