## Slide 1
Building Management System
Proposal for the Kingsford Hotel Bacolod — BMS Rehabilitation (A/B run) Project
Submitted to Megaworld Corporation · Manhattan Street, The Upper East, Bacolod City · 2026-04-28

## Slide 2
Agenda
• 1. Our understanding of your project
• 2. System architecture overview
• 3. Scope of supply (equipment + services)
• 4. Project schedule
• 5. Quality and commissioning approach
• 6. Commercial summary
• 7. Stated assumptions and clarifications
• 8. Why partner with us
• 9. Next steps

## Slide 3
01
Our Understanding of the Project

## Slide 4
Kingsford Hotel Bacolod — at a glance
A Megaworld Corporation new-construction development requiring a comprehensive BMS
Building characteristics
• Multi-floor hotel in Bacolod City • Casino at the 2nd Level with dedicated MVAC • Amenity facilities at the 3rd Floor • Hotel guestrooms above the 3rd Floor • Food and beverage outlets with kitchen scope • Standard hotel back-of-house services
Mechanical / electrical services in BMS scope
• Centralised chilled-water plant (Ground) • Hot-water generation plants (LZ + Roofdeck) • Steam boilers for laundry (Lower Ground) • Distributed ventilation across 5 zones • Cooling towers at Roofdeck • Multifunction electrical metering across 13 feeders

## Slide 5
Reference Documents
Our proposal is grounded in your project's official documentation
• BMS Points list (TUEC) — sheets BMS-01, BMS-02, BMS-03
◦ Process and Instrumentation Diagrams + I/O point tabulation
◦ By R.J. Calpo & Company (Engr. Reynaldo J. Calpo, PME License No. 0001784)
◦ Construction Bulletin, dated October 2025
• EE Plan (TUEC) — Construction Bulletin No.8
◦ Revised electrical drawings, load schedules, power riser
◦ By Mario A. Alix Philippines, Inc., dated 5 November 2025
• Megaworld MC Standards — DRC-004-2024 Revised BMS Standards
◦ Mechanical and Plumbing Points Lists (CONDOTELS baseline)
• Customer enquiry letter (Requirement.rtf)
◦ Defines the explicit scope statement

## Slide 6
02
System Architecture

## Slide 7
Three-tier BMS Architecture
Open-standards, redundant, web-accessible, future-ready
• TIER 1 — HEAD-END (BMS Server Room)
◦ Redundant primary–standby BMS servers with 30-min UPS protection
◦ Two operator workstations (chief engineer + front desk / shift staff)
◦ Graphics PC + 55-inch control-room display
◦ BACnet-IP server software with energy-savings optimization module
• TIER 2 — NETWORK (Building backbone)
◦ Isolated BMS LAN with single uplink to corporate network
◦ 1 core managed switch + 6 edge switches across the building
◦ OM3 fiber backbone to floor IDFs; Cat6 to BACnet-IP equipment
• TIER 3 — FIELD (Plant rooms and floor zones)
◦ 18 BMS field panels with ~30 DDC controllers
◦ BACnet-IP-native equipment: chillers, AHUs, DOAS, PAHU
◦ Modbus power meters, BTU meter via Modbus-IP gateways

## Slide 8
Scope at a Glance
The BMS engineering basis in numbers
762
BMS I/O points
125
Equipment instances
6
Field panels
18
DDC controllers
9
Subsystems
17 IDFs
Locations served
6,810 m
Total cable estimated
13
Power meters
35
Operator graphic pages

## Slide 9
03
Scope of Supply

## Slide 10
Subsystem Coverage
Every BMS-monitored subsystem in the project
Subsystem | Equipment | I/O Points
Chilled Water Plant + Cooling Towers | 13 (3 chillers, 4 PCHWP, 3 COMP, 3 CTs) | 159
Basement-Podium BOH AHUs | 3 confirmed (CHWP-1.1/1.2/1.3 at GND) | 51
Plumbing/Sanitary Hotwater | 20 (calorifiers ×6 + heat pumps ×6 + recirc ×6 + headers) | 48
General Ventilation (5 zones) | 68 exhaust fans (GF, 2nd, 3rd Amenity, Basement, Roofdeck) | 204
Boiler / Laundry | 2 steam boilers (SB-1, SB-2) at Lower Ground | 32
Casino MVAC + Hotel/Roofdeck DOAS | 3 (DOAS-2W + DOAS-RD.1/2 with ozonizers) | 78
AHU 2nd Level + Roofdeck PAHU | 6 (AHU-2M.1/2 + Ozonizers ×2 + PAHU-RD.1/2) | 66
Power Metering / EE Integration | 13 meters (3 main + 10 sub-feeder) | 78

## Slide 11
Equipment Highlights
Tier-1 BACnet/IP-native equipment — Megaworld portfolio standards
Head-end and network
• 2× redundant BMS servers (HE-SVR-01/02) • 2× operator workstations • 1× graphics PC + 55-inch commercial display • 3 kVA UPS, 30-min runtime • Server room rack + cabling + KVM + alarm printer • Software: server + 3 client + energy module + graphics editor • 1 core managed switch + 6 edge switches • 300 m OM3 fiber riser + 14 transceivers • Cat6 + BACnet-IP integration to all equipment
Field panels and devices
• 18 BMS field panels (IP54 wall-mount) • ~30 DDC controllers (mix of network + I/O) • I/O modules: 9 AI + 3 AO + 17 DI + 2 DO • Surge protection on all panels • ~150 BMS-supplied sensors (T, RH, P, flow, CO2, CO, VOC) • 13 multifunction power meters + 39 CTs • 2 Modbus serial-to-IP gateways • 1 plant-level BTU meter • ~6,810 m total cable + branch conduit

## Slide 12
04
Project Schedule

## Slide 13
16-Week Project Schedule
From Purchase Order to Handover
Wk | Phase | Key activities
1 | Mobilization + Engineering | Site mobilization, kick-off, MEP coordination
2-4 | Engineering & Submittals | Panel layouts, IO list, control sequences, network design
4 | Procurement | Long-lead supply orders placed (chillers, server, UPS)
5 | Factory Acceptance Test | FAT in vendor facility prior to site mobilization
6 | Material Delivery | All supply on site
7-12 | Installation | Containment → cable pulling → panels → devices → head-end
12 | Pre-Commissioning | Power-up, smoke tests, panel verification
13 | Point-to-Point Testing | 523 physical I/O verified panel-by-panel
14 | Functional Testing | 135 equipment functional sequences
15 | Integrated + SAT | 8 cross-system sequences + Owner Site Acceptance Test
16 | Training + Handover | 16 hours operator training, as-built docs, warranty start

## Slide 14
Resourcing Plan
Peak headcount of 11 personnel during weeks 9–10; total project effort 4,648 hours
Manpower mix
• Project Manager × 1 (full duration) • Engineering: 2 BMS engineers during design phase • Wireman/Electrician crew of 4–6 during installation • BMS Technician crew of 1–3 during commissioning • Graphics Engineer × 1 during programming weeks • Total person-days: 581 • Total project hours: 4,648
Effort by phase
• Engineering & Design (1.2): 320 hr • Project Management (1.1, 3.1): 720 hr • Submittals & FAT (1.3, 1.4): 120 hr • Installation (3.0): 3,336 hr • Programming (4.1): 219 hr • Graphics (4.2): 140 hr • Testing & Commissioning (5.x): 313 hr • SAT + Docs + Training (5.5–7, 6.x): 200 hr Total: 4,648 hours

## Slide 15
05
Quality and Commissioning

## Slide 16
Quality Framework
Engineering, factory, and site quality stages
• ENGINEERING QUALITY
◦ All submittals peer-reviewed; panel general arrangement drawings signed by engineer of record
• MATERIAL QUALITY
◦ Tier-1 brand selection; factory-tested controllers; FRLS-compliant cabling per fire code
• FACTORY ACCEPTANCE TEST (Week 5)
◦ Demonstration of programming, graphics, BACnet integration, redundancy failover at vendor facility
• INSTALLATION QUALITY
◦ Site supervision by BMS technician at all times during cable pulling and panel installation
• COMMISSIONING (Weeks 12–15)
◦ 100% P2P coverage of physical I/O — every point calibrated and verified
◦ 100% functional test coverage of equipment — every sequence verified
◦ Cross-system integrated commissioning — all chiller-AHU-DOAS-energy savings sequences
• SITE ACCEPTANCE TEST (Week 15)
◦ Live demonstration with Owner's representative; warranty commences upon SAT signature

## Slide 17
Warranty and Post-handover Support
Two-year coverage from handover
• WARRANTY PERIOD
◦ 1-year manufacturer warranty (per equipment vendor)
◦ 1-year on-site defect liability by ourselves
• DURING ON-SITE DEFECT LIABILITY
◦ Site visits in response to fault calls within 24 hours of report
◦ Replacement of any defective BMS-supplied component at no charge
◦ Programming or graphics adjustments at no charge
◦ Software updates within manufacturer's release schedule
◦ Telephone support during business hours
• OPTIONAL EXTENSIONS
◦ 1-year preventive maintenance contract — quote on request
◦ Vendor factory training — quote on request
◦ Spare-parts inventory beyond warranty stock — quote on request

## Slide 18
06
Commercial Summary

## Slide 19
Pricing Summary
All values in Philippine Pesos (PHP)
Item | PHP
Base proposal cost (material + labor + services) | 15,548,700
Overhead and margin (20%) | 3,109,740
Contingency reserve (7.5%) | 1,399,383
Sub-total before VAT | 20,057,823
VAT (12%) | 2,406,939
GRAND TOTAL (VAT-inclusive) | 22,464,762

## Slide 20
Cost Breakdown by Section
Material supply represents the largest cost component (~71%)
Section | PHP | % of base
1.0 Project Management & Engineering | 1,688,000 | 10.9%
2.0 Material Supply | 11,069,210 | 71.2%
3.0 Installation | 1,696,070 | 10.9%
4.0 Programming & Configuration | 523,560 | 3.4%
5.0 Testing & Commissioning | 480,660 | 3.1%
6.0 Training & Handover | 91,200 | 0.6%
Base total | 15,548,700 | 100.0%

## Slide 21
Proposed Payment Milestones
Aligned with manpower and material delivery cycles
% | Milestone | Trigger
10% | Mobilization advance | Upon PO + signed contract
15% | Engineering complete | Submittals approved (Week 4)
25% | Long-lead materials delivered | Site delivery (Weeks 5–6)
20% | Standard materials delivered | Site delivery (Weeks 6–7)
15% | Installation complete | Mech-ready at Week 12
10% | T&C complete + SAT | Customer SAT signed (Week 15)
5% | Handover + warranty start | Documentation accepted (Week 16)

## Slide 22
Optional Items (Quote on Request)
Available add-ons not in base proposal
• 1-year preventive maintenance contract (post-warranty)
◦ Quarterly site visits + emergency call-out + spare-parts replenishment
• FDAS (Fire Detection & Alarm) integration
◦ BACnet/Modbus from fire panel + smoke control sequences
• PMS (Property Management System) integration
◦ Guestroom occupancy → BMS for fan-coil unit control
• Additional administrator training (8 hr session)
◦ ~PHP 30,000 per session
• Vendor factory training (overseas)
◦ Quote on request, varies by vendor and location
• Spare-parts inventory beyond warranty stock
◦ 5% of critical-replacement items, quote on request

## Slide 23
07
Stated Assumptions

## Slide 24
Top Stated Assumptions
These form the basis of our proposal — confirmation will refine accordingly
Item | Default assumed | Sensitivity
Project stage | Greenfield (per technical docs) | ±30% if retrofit
Schedule duration | 16 weeks PO → handover | +20-30% if shorter
Working hours | Standard daytime construction | +15% if night-work
Per-guestroom FCUs | Not in scope | +30-40% if confirmed
FDAS / PMS / CCTV / ACS integration | Not in scope | +PHP 200K-500K each
Brand selection | Tier-1 BACnet IP | ±15% per Q-013
Network architecture | Isolated BMS LAN, flat /24 | Minor refinement
Cable lengths | 30 m avg run, 80 m/floor trunk | Refined post-Q-005/Q-008
Commercial terms | 30-day net, 10% retention, 1+1 yr warranty | Refined per Q-014
Training scope | 16 hr operator, included | Admin/factory training as options

## Slide 25
Open Clarification Items (RFI)
Your responses will refine our base proposal
• P1 — CRITICAL (cost-swing potential > 10%)
◦ Confirm project stage (greenfield, per technical evidence)
◦ Confirm required project duration (16 weeks assumed)
• P2 — IMPORTANT (refines pricing)
◦ Confirm contracting entity, architectural / mechanical / electrical drawings, working hours
• P3 — USEFUL (refines pricing precision)
◦ Confirm 'TUEC' project code, integration scope, brand standardization, commercial terms
◦ Confirm training scope, maintenance scope, CONDOTELS standard alignment
◦ Confirm FCU scope, booster pump scope, complete BOH AHU schedule
•
• Detailed RFI list (19 questions) is provided as an appendix and as a separate Word document.

## Slide 26
08
Why Partner With Us

## Slide 27
Why Partner With Us
What sets this proposal apart
What we bring
• ENGINEERING DEPTH Every quantity in this proposal traces back to your project documentation. • OPEN STANDARDS BACnet/IP and Modbus throughout — no vendor lock-in, future-proof. • OPERATIONAL RELIABILITY Redundant servers, UPS-backed head-end, isolated BMS LAN. • TRANSPARENT PRICING Detailed BOQ with 86 line items, peer-reviewable rates.
How we work
• AUDITABLE BASIS Full working-doc package (BOQ, equipment, cable, panel schedules) provided. • EXPLICIT ASSUMPTIONS 19 stated assumptions with cost-impact tags — no hidden surprises. • ENERGY-SAVINGS DRIVEN Pre-engineered chiller plant sequencing + demand control. • PROACTIVE COMMUNICATION 19 customer clarifications surfaced upfront for joint resolution.

## Slide 28
Proposal Documentation Package
Comprehensive supporting documents accompany this presentation
Document | Format | Content
Initial Overview | PDF | Executive summary + headline numbers
Standard Proposal | PDF | Customer-facing 30-page narrative
Comprehensive Proposal | PDF + DOCX | Full enterprise-grade proposal with all appendices
Bill of Quantities | Excel | 86 line items, 11 sheets, by-section breakdowns
I/O List | Excel | 716 BMS I/O points with full metadata
Equipment Takeoff | Excel | 135 equipment instances with location/panel/supplier
Cable Schedule | Excel | 200 cables, 6,810 m, by-panel breakdown
Panel Schedule | Excel | 18 panels with I/O density + power
Open Items / RFI | Word | 19 customer clarifications with cover letter
Stated Assumptions | Word | 19 active assumptions with rationale
This Presentation | PowerPoint | Customer-facing proposal walkthrough

## Slide 29
09
Next Steps

## Slide 30
Proposed Next Steps
How we move from proposal to project execution
• 1. YOUR REVIEW
◦ Internal review by Megaworld engineering and commercial teams
◦ Review of supporting working documents (Excel + Word) provided in package
• 2. CLARIFICATION RESPONSES
◦ Your team responds to the 19 clarification items (RFI document)
◦ Priority: 2 P1 items first (project stage and schedule)
• 3. PROPOSAL REFINEMENT (optional)
◦ Based on your responses, we issue a revised proposal with refined pricing
◦ Typically 5–7 working days for revised proposal
• 4. COMMERCIAL NEGOTIATION
◦ Final commercial terms (payment schedule, retention, warranty)
• 5. PROJECT KICK-OFF
◦ Upon Purchase Order, mobilization begins Week 1
◦ Engineering deliverables start within 1 week of PO

## Slide 31
Thank you
We are committed to delivering a Building Management System that meets the operational and energy-efficiency objectives of the Kingsford Hotel Bacolod project.
We welcome your questions and look forward to your response.