## Summary
A2 — Equipment Takeoff, Audit View
Project | Kingsford Hotel Bacolod — BMS
Canonical source | A2-equipment-takeoff.yaml
How to record corrections | Edit the canonical YAML directly — add a verification: block to the affected row(s)
Totals
Total equipment instances | 132
Equipment classes | 23
Locations | 17
Verification status
Status | Count | % of total
verified | 0 | 0%
needs_correction | 0 | 0%
uncertain | 0 | 0%
unverified | 132 | 100%
⚠ Known weak points
Verify quantities and locations against mechanical / electrical drawings. The 'Make/Model' field is a generic class default — supplier RFQ refines.
How corrections flow
Edit A2-equipment-takeoff.yaml — add a verification: block to the affected row when location or count is confirmed/corrected.

## By Class
Equipment class | Count
Exhaust Fan (Toilet) | 53
Multifunction Power Meter (Feeder) | 10
Exhaust Fan (General) | 8
Precooled Air Handling Unit | 7
Heat Pump | 6
Calorifier (Hot Water Storage Tank) | 6
Recirculating Pump | 6
BTU Meter | 5
AHU (Chilled-Water-Served) | 4
Chiller (Package Water-Cooled) | 3
Cooling Tower | 3
Condenser Water Pump | 3
DOAS Unit | 3
Primary CHW Pump | 3
AHU (Modulating CHW-served) | 2
Ozone Generator (UV-light or Corona) | 2
Steam Boiler | 2
CHW Bypass Header | 1
CHW Return Main Header | 1
CHW Supply Main Header | 1
Cooling Tower (Common) | 1
Hot Water Header Set | 1
Multifunction Power Meter (Main) | 1
TOTAL | 132

## By Location
Location | Count
3rd Floor Amenity | 26
2nd Level Mechanical Room | 20
Basement 1 | 16
Roof Deck Mechanical | 14
Lower Ground HW Plant | 10
Ground Floor Lobby | 9
Roof Deck HW Plant | 9
Roof Deck | 6
2nd Floor BOH | 5
Ground Floor | 4
2nd Floor Casino MVAC Room | 3
2nd Floor Casino | 3
Lower Ground Laundry | 3
Basement 1 BOH | 1
Ground Floor BOH | 1
Ground Floor Mezzanine BOH | 1
Main Switchgear Room | 1

## Detail
ID | Class | Location | Panel | Primary C/O | Status | Verified by | Date | Drawing ref | Notes
AHU-2F-1 | AHU (Chilled-Water-Served) | 2nd Floor BOH | BMS-PNL-2F-CASINO | BMS Contractor | unverified
AHU-2M.1 | AHU (Modulating CHW-served) | 2nd Floor Casino MVAC Room | BMS-PNL-2F-CASINO | BMS Contractor | unverified
AHU-2M.2 | AHU (Modulating CHW-served) | 2nd Floor Casino MVAC Room | BMS-PNL-2F-CASINO | BMS Contractor | unverified
AHU-B1-1 | AHU (Chilled-Water-Served) | Basement 1 BOH | BMS-PNL-B1 | BMS Contractor | unverified
AHU-GF-1 | AHU (Chilled-Water-Served) | Ground Floor BOH | BMS-PNL-GF | BMS Contractor | unverified
AHU-GFM-1 | AHU (Chilled-Water-Served) | Ground Floor Mezzanine BOH | BMS-PNL-GF | BMS Contractor | unverified
BTU-1 | BTU Meter | 2nd Level Mechanical Room | BMS-PNL-LG-CHILLER | BMS Contractor | unverified
BTU-2 | BTU Meter | 2nd Level Mechanical Room | BMS-PNL-LG-CHILLER | BMS Contractor | unverified
BTU-3 | BTU Meter | 2nd Level Mechanical Room | BMS-PNL-LG-CHILLER | BMS Contractor | unverified
BTU-4 | BTU Meter | 2nd Level Mechanical Room | BMS-PNL-LG-CHILLER | BMS Contractor | unverified
BTU-5 | BTU Meter | 2nd Level Mechanical Room | BMS-PNL-LG-CHILLER | BMS Contractor | unverified
CH-1 | Chiller (Package Water-Cooled) | 2nd Level Mechanical Room | BMS-PNL-LG-CHILLER | Equipment Supplier | unverified
CH-2 | Chiller (Package Water-Cooled) | 2nd Level Mechanical Room | BMS-PNL-LG-CHILLER | Equipment Supplier | unverified
CH-3 | Chiller (Package Water-Cooled) | 2nd Level Mechanical Room | BMS-PNL-LG-CHILLER | Equipment Supplier | unverified
CHW-BYPASS | CHW Bypass Header | 2nd Level Mechanical Room | BMS-PNL-LG-CHILLER | BMS Contractor | unverified
CHW-HDR-R | CHW Return Main Header | 2nd Level Mechanical Room | BMS-PNL-LG-CHILLER | BMS Contractor | unverified
CHW-HDR-S | CHW Supply Main Header | 2nd Level Mechanical Room | BMS-PNL-LG-CHILLER | BMS Contractor | unverified
CT-1 | Cooling Tower | Roof Deck Mechanical | BMS-PNL-RD-CT | BMS Contractor | unverified
CT-2 | Cooling Tower | Roof Deck Mechanical | BMS-PNL-RD-CT | BMS Contractor | unverified
CT-3 | Cooling Tower | Roof Deck Mechanical | BMS-PNL-RD-CT | BMS Contractor | unverified
CT-COMMON | Cooling Tower (Common) | Roof Deck Mechanical | BMS-PNL-RD-CT | BMS Contractor | unverified
CWP-1 | Condenser Water Pump | 2nd Level Mechanical Room | BMS-PNL-LG-CHILLER | Equipment Supplier | unverified
CWP-2 | Condenser Water Pump | 2nd Level Mechanical Room | BMS-PNL-LG-CHILLER | Equipment Supplier | unverified
CWP-3 | Condenser Water Pump | 2nd Level Mechanical Room | BMS-PNL-LG-CHILLER | Equipment Supplier | unverified
DOAS-2F-CASINO | DOAS Unit | 2nd Floor Casino MVAC Room | BMS-PNL-2F-CASINO | BMS Contractor | unverified
DOAS-RD1 | DOAS Unit | Roof Deck Mechanical | BMS-PNL-RD-MECH | BMS Contractor | unverified
DOAS-RD2 | DOAS Unit | Roof Deck Mechanical | BMS-PNL-RD-MECH | BMS Contractor | unverified
EF-1 | Exhaust Fan (General) | Roof Deck | BMS-PNL-RD-MECH | Equipment Supplier | unverified
EF-1.2A | Exhaust Fan (General) | Ground Floor Lobby | BMS-PNL-GF | Equipment Supplier | unverified
EF-1MR.1 | Exhaust Fan (General) | Ground Floor Lobby | BMS-PNL-GF | Equipment Supplier | unverified
EF-1STO.1 | Exhaust Fan (General) | Ground Floor Lobby | BMS-PNL-GF | Equipment Supplier | unverified
EF-LPG.1 | Exhaust Fan (General) | Ground Floor Lobby | BMS-PNL-GF | Equipment Supplier | unverified
EF-MRF.1 | Exhaust Fan (General) | Ground Floor Lobby | BMS-PNL-GF | Equipment Supplier | unverified
EF-RD.1 | Exhaust Fan (General) | Roof Deck | BMS-PNL-RD-MECH | Equipment Supplier | unverified
EF-RD.2 | Exhaust Fan (General) | Roof Deck | BMS-PNL-RD-MECH | Equipment Supplier | unverified
HP-HZ-1 | Heat Pump | Roof Deck HW Plant | BMS-PNL-RD-MECH | Equipment Supplier | unverified
HP-HZ-2 | Heat Pump | Roof Deck HW Plant | BMS-PNL-RD-MECH | Equipment Supplier | unverified
HP-HZ-3 | Heat Pump | Roof Deck HW Plant | BMS-PNL-RD-MECH | Equipment Supplier | unverified
HP-LZ-1 | Heat Pump | Lower Ground HW Plant | BMS-PNL-LG-PLUMB | Equipment Supplier | unverified
HP-LZ-2 | Heat Pump | Lower Ground HW Plant | BMS-PNL-LG-PLUMB | Equipment Supplier | unverified
HP-LZ-3 | Heat Pump | Lower Ground HW Plant | BMS-PNL-LG-PLUMB | Equipment Supplier | unverified
HW-HEADERS | Hot Water Header Set | Lower Ground HW Plant | BMS-PNL-LG-PLUMB | BMS Contractor | unverified
HWT-HZ-1 | Calorifier (Hot Water Storage Tank) | Roof Deck HW Plant | BMS-PNL-RD-MECH | BMS Contractor | unverified
HWT-HZ-2 | Calorifier (Hot Water Storage Tank) | Roof Deck HW Plant | BMS-PNL-RD-MECH | BMS Contractor | unverified
HWT-HZ-3 | Calorifier (Hot Water Storage Tank) | Roof Deck HW Plant | BMS-PNL-RD-MECH | BMS Contractor | unverified
HWT-LZ-1 | Calorifier (Hot Water Storage Tank) | Lower Ground HW Plant | BMS-PNL-LG-PLUMB | BMS Contractor | unverified
HWT-LZ-2 | Calorifier (Hot Water Storage Tank) | Lower Ground HW Plant | BMS-PNL-LG-PLUMB | BMS Contractor | unverified
HWT-LZ-3 | Calorifier (Hot Water Storage Tank) | Lower Ground HW Plant | BMS-PNL-LG-PLUMB | BMS Contractor | unverified
ION-2F-1 | Ozone Generator (UV-light or Corona) | 2nd Floor Casino | BMS-PNL-2F-CASINO | Equipment Supplier | unverified
ION-2F-2 | Ozone Generator (UV-light or Corona) | 2nd Floor Casino | BMS-PNL-2F-CASINO | Equipment Supplier | unverified
PAHU-01 | Precooled Air Handling Unit | Roof Deck Mechanical | BMS-PNL-RD-MECH | BMS Contractor | unverified
PAHU-02 | Precooled Air Handling Unit | Roof Deck Mechanical | BMS-PNL-RD-MECH | BMS Contractor | unverified
PAHU-03 | Precooled Air Handling Unit | Roof Deck Mechanical | BMS-PNL-RD-MECH | BMS Contractor | unverified
PAHU-04 | Precooled Air Handling Unit | Roof Deck Mechanical | BMS-PNL-RD-MECH | BMS Contractor | unverified
PAHU-05 | Precooled Air Handling Unit | Roof Deck Mechanical | BMS-PNL-RD-MECH | BMS Contractor | unverified
PAHU-06 | Precooled Air Handling Unit | Roof Deck Mechanical | BMS-PNL-RD-MECH | BMS Contractor | unverified
PAHU-07 | Precooled Air Handling Unit | Roof Deck Mechanical | BMS-PNL-RD-MECH | BMS Contractor | unverified
PCHWP-1 | Primary CHW Pump | 2nd Level Mechanical Room | BMS-PNL-LG-CHILLER | Equipment Supplier | unverified
PCHWP-2 | Primary CHW Pump | 2nd Level Mechanical Room | BMS-PNL-LG-CHILLER | Equipment Supplier | unverified
PCHWP-3 | Primary CHW Pump | 2nd Level Mechanical Room | BMS-PNL-LG-CHILLER | Equipment Supplier | unverified
PM-CASINO-FB | Multifunction Power Meter (Feeder) | 2nd Floor Casino | BMS-PNL-2F-CASINO | BMS Contractor | unverified
PM-CHILLER-1 | Multifunction Power Meter (Feeder) | 2nd Level Mechanical Room | BMS-PNL-LG-CHILLER | BMS Contractor | unverified
PM-CHILLER-2 | Multifunction Power Meter (Feeder) | 2nd Level Mechanical Room | BMS-PNL-LG-CHILLER | BMS Contractor | unverified
PM-CHILLER-3 | Multifunction Power Meter (Feeder) | 2nd Level Mechanical Room | BMS-PNL-LG-CHILLER | BMS Contractor | unverified
PM-ELEVATOR | Multifunction Power Meter (Feeder) | Ground Floor | BMS-PNL-GF | BMS Contractor | unverified
PM-KITCHEN-2F | Multifunction Power Meter (Feeder) | 2nd Floor BOH | BMS-PNL-2F-CASINO | BMS Contractor | unverified
PM-LAUNDRY-LG | Multifunction Power Meter (Feeder) | Lower Ground Laundry | BMS-PNL-LG-PLUMB | BMS Contractor | unverified
PM-LIGHTING-GUEST | Multifunction Power Meter (Feeder) | 3rd Floor Amenity | BMS-PNL-3F | BMS Contractor | unverified
PM-LOBBY-GF | Multifunction Power Meter (Feeder) | Ground Floor | BMS-PNL-GF | BMS Contractor | unverified
PM-MAIN | Multifunction Power Meter (Main) | Main Switchgear Room | BMS-PNL-GF | BMS Contractor | unverified
PM-ROOFDECK-MECH | Multifunction Power Meter (Feeder) | Roof Deck Mechanical | BMS-PNL-RD-MECH | BMS Contractor | unverified
RP-HZ-1 | Recirculating Pump | Roof Deck HW Plant | BMS-PNL-RD-MECH | Equipment Supplier | unverified
RP-HZ-2 | Recirculating Pump | Roof Deck HW Plant | BMS-PNL-RD-MECH | Equipment Supplier | unverified
RP-HZ-3 | Recirculating Pump | Roof Deck HW Plant | BMS-PNL-RD-MECH | Equipment Supplier | unverified
RP-LZ-1 | Recirculating Pump | Lower Ground HW Plant | BMS-PNL-LG-PLUMB | Equipment Supplier | unverified
RP-LZ-2 | Recirculating Pump | Lower Ground HW Plant | BMS-PNL-LG-PLUMB | Equipment Supplier | unverified
RP-LZ-3 | Recirculating Pump | Lower Ground HW Plant | BMS-PNL-LG-PLUMB | Equipment Supplier | unverified
SB-1 | Steam Boiler | Lower Ground Laundry | BMS-PNL-LG-PLUMB | Equipment Supplier | unverified
SB-2 | Steam Boiler | Lower Ground Laundry | BMS-PNL-LG-PLUMB | Equipment Supplier | unverified
TEF-1.1 | Exhaust Fan (Toilet) | Ground Floor Lobby | BMS-PNL-GF | Equipment Supplier | unverified
TEF-1.2 | Exhaust Fan (Toilet) | Ground Floor Lobby | BMS-PNL-GF | Equipment Supplier | unverified
TEF-1.3 | Exhaust Fan (Toilet) | Ground Floor Lobby | BMS-PNL-GF | Equipment Supplier | unverified
TEF-1.4 | Exhaust Fan (Toilet) | Ground Floor Lobby | BMS-PNL-GF | Equipment Supplier | unverified
TEF-2.1 | Exhaust Fan (Toilet) | 2nd Floor BOH | BMS-PNL-2F-CASINO | Equipment Supplier | unverified
TEF-2.3 | Exhaust Fan (Toilet) | 2nd Floor BOH | BMS-PNL-2F-CASINO | Equipment Supplier | unverified
TEF-2B.3 | Exhaust Fan (Toilet) | 2nd Floor BOH | BMS-PNL-2F-CASINO | Equipment Supplier | unverified
TEF-3A.1 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3A.2 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3B | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3C.1 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3C.2 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3D.1 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3D.10 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3D.11 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3D.12 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3D.13 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3D.14 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3D.15 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3D.16 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3D.17 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3D.18 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3D.19 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3D.2 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3D.20 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3D.3 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3D.4 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3D.5 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3D.6 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3D.7 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3D.8 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-3D.9 | Exhaust Fan (Toilet) | 3rd Floor Amenity | BMS-PNL-3F | Equipment Supplier | unverified
TEF-B.1 | Exhaust Fan (Toilet) | Basement 1 | BMS-PNL-B1 | Equipment Supplier | unverified
TEF-B.10 | Exhaust Fan (Toilet) | Basement 1 | BMS-PNL-B1 | Equipment Supplier | unverified
TEF-B.11 | Exhaust Fan (Toilet) | Basement 1 | BMS-PNL-B1 | Equipment Supplier | unverified
TEF-B.12 | Exhaust Fan (Toilet) | Basement 1 | BMS-PNL-B1 | Equipment Supplier | unverified
TEF-B.13 | Exhaust Fan (Toilet) | Basement 1 | BMS-PNL-B1 | Equipment Supplier | unverified
TEF-B.14 | Exhaust Fan (Toilet) | Basement 1 | BMS-PNL-B1 | Equipment Supplier | unverified
TEF-B.15 | Exhaust Fan (Toilet) | Basement 1 | BMS-PNL-B1 | Equipment Supplier | unverified
TEF-B.16 | Exhaust Fan (Toilet) | Basement 1 | BMS-PNL-B1 | Equipment Supplier | unverified
TEF-B.2 | Exhaust Fan (Toilet) | Basement 1 | BMS-PNL-B1 | Equipment Supplier | unverified
TEF-B.3 | Exhaust Fan (Toilet) | Basement 1 | BMS-PNL-B1 | Equipment Supplier | unverified
TEF-B.4 | Exhaust Fan (Toilet) | Basement 1 | BMS-PNL-B1 | Equipment Supplier | unverified
TEF-B.5 | Exhaust Fan (Toilet) | Basement 1 | BMS-PNL-B1 | Equipment Supplier | unverified
TEF-B.6 | Exhaust Fan (Toilet) | Basement 1 | BMS-PNL-B1 | Equipment Supplier | unverified
TEF-B.7 | Exhaust Fan (Toilet) | Basement 1 | BMS-PNL-B1 | Equipment Supplier | unverified
TEF-B.8 | Exhaust Fan (Toilet) | Basement 1 | BMS-PNL-B1 | Equipment Supplier | unverified
TEF-B.9 | Exhaust Fan (Toilet) | Basement 1 | BMS-PNL-B1 | Equipment Supplier | unverified
TEF-GS.1 | Exhaust Fan (Toilet) | Ground Floor | BMS-PNL-GF | Equipment Supplier | unverified
TEF-GS.2 | Exhaust Fan (Toilet) | Ground Floor | BMS-PNL-GF | Equipment Supplier | unverified
TEF-RD.1 | Exhaust Fan (Toilet) | Roof Deck | BMS-PNL-RD-MECH | Equipment Supplier | unverified
TEF-RD.2 | Exhaust Fan (Toilet) | Roof Deck | BMS-PNL-RD-MECH | Equipment Supplier | unverified
TEF-RD.3 | Exhaust Fan (Toilet) | Roof Deck | BMS-PNL-RD-MECH | Equipment Supplier | unverified

## Verification schema
How to record verification / corrections in A2-equipment-takeoff.yaml
Find the affected row in the YAML by ID (Detail sheet column A) and add a verification: block:
- id: AHU-01
verification: # ADDED by team
status: needs_correction # unverified ¦ verified ¦ needs_correction ¦ uncertain
corrected_location: 3rd Floor Mech Room # team's measured / confirmed value
verified_by: J. Cruz
verified_date: 2026-05-10
drawing_ref: "EE-09 grid B-2"
notes: ""
After saving, re-run: python3 _playbook/tools/generate-deliverables.py <project>
Corrections propagate to B4 manhours, BOQ, and final deliverables automatically.
Recommended verification methods (priority order):
1. Site walkthrough with measurement (most accurate; for cable lengths, after structural completion).
2. Properly-scaled architectural drawings.
3. Mechanical contractor's tray layout combined with BMS panel locations.
4. A-001 default with ±20% contingency in BOQ — last resort.