Table of Contents

# Internal Team Notes — 2026-04-kingsford-bms-AB4

Audience: the proposal team running the next pass on this project.

This document compiles actionable items pulled from the project’s working artifacts. Each section is what to do next — verify, refine, or reconsider — to improve the proposal before it goes to the customer or as part of an RFQ-response cycle.

Sources compiled:

- 07-assumptions.md — assumptions to verify or refine

- 08-customer-clarifications.md — questions to send the customer

- 99-decision-log.md — decisions worth revisiting

- 03-doc-inventory.md — gap analysis on customer inputs

- 05-working-docs/A3-cable-schedule.yaml — cable-length fallbacks to verify

- 05-working-docs/D3-risk-register.md — project risks (if present)

- 09-rfq-package/ — RFQ packages (cost-reduction via competitive bidding)

## 1. Customer clarifications (RFI list)

0 open questions to send the customer. Each has a documented default assumption with cost / scope impact. Resolving these is the highest-leverage path to refining the proposal — every answered Q-NNN may flip an open assumption from Assumed to Confirmed and reduce contingency.

## 2. Verification action items (against drawings, on site, with vendors)

### Cable lengths — fallback rows to verify

Cables tagged legacy_fallback, typical_range:*, or fallback_a001 use agent-reasoned typical-range estimates rather than direct drawing measurements. These are the audit-XLSX rows the team should prioritize when the next set of drawings lands or when site walkthroughs become possible.

| Method tag | Count | Sample row ID |
| --- | --- | --- |
| typical_range:boh_same_floor | 80 | C0001 |
| typical_range:roofdeck_plant_area | 63 | C0029 |
| typical_range:plant_room_same_room | 47 | C0019 |
| typical_range:panel_power_feed | 8 | P0202 |
| unknown | 5 | T0195 |
| typical_range:guestroom_corridor | 4 | C0161 |
| agent_specified | 2 | T0200 |

Open 13-A3-cable-schedule-AUDIT.xlsx to filter and prioritize.

### Other verification items

- Equipment counts — verify against mechanical floor plans where the agent inferred quantities (see open assumptions where Status: Open and category contains ‘count’).

- Panel locations — confirm against architectural drawings and walk the building if accessible.

- Drawing scale calibrations — if any A-NNN entries record drawing-scale calibration assumptions (e.g., grid-bay calibration), spot-check against a second known dimension before the proposal goes out.

- Vendor specifications — for every Equipment Supplier C/O cable / interface, confirm that the supplier’s panel architecture matches the assumed BMS-side interface (HLI vs. hardwired DI/DO).

## 3. Cost-reduction opportunities

### RFQ packages — competitive bidding

The agent prepared 12 RFQ packages categorized by supplier type. Issuing all of them and comparing 3+ quotes per package is the standard cost-reduction lever. Especially impactful for high-value categories:

- bms-controllers-and-panels — typically 5–15% savings vs. catalog pricing on competitive bid

- field-sensors-hvac — typically 5–15% savings vs. catalog pricing on competitive bid

- head-end-servers-workstations — typically 5–15% savings vs. catalog pricing on competitive bid

- network-active — typically 5–15% savings vs. catalog pricing on competitive bid

- power-meters — typically 5–15% savings vs. catalog pricing on competitive bid

- valves-actuators — typically 5–15% savings vs. catalog pricing on competitive bid

Full list in 09-rfq-package/. Send these as soon as the proposal’s commercial side is firm — supplier turnaround is typically 2–4 weeks.

### Other cost levers

- Cable specifications — confirm with the customer whether the assumed jacket rating (e.g., FRLS) is mandated or whether a less-specified cable is acceptable in non-occupied spaces. Material cost difference can be 10–20% on cabling.

- Spare-conductor strategy — current strategy provides 15–25% spares per I/O class. If the customer is willing to accept lower spare margins (commit to the I/O list as-final), cable size drops and material cost reduces 5–10%.

- Make/model consolidation — RFQ packages currently call for spec-level equivalent items. If the customer accepts a single-vendor list (one controller brand, one valve brand), the team can negotiate volume discounts. Document any such consolidation in a new Q-NNN.

- Owner-furnished items — review C1 contractor/owner matrix; items currently assigned to BMS scope that the owner could supply directly (e.g., off-the-shelf workstations, network switches if customer has IT preferences) reduce BMS material markup.

## 4. Risks and decisions to revisit

### Risk register highlights

Open risks from D3-risk-register.md worth re-evaluating before issue:

- R-01 — Stage misclassification (rehab vs. greenfield) | Low | High

- R-02 — Plumbing scope expands beyond hot water | Medium | Medium

- R-03 — Guestroom FCU controls in BMS scope (~280 rooms) | Medium | High

- R-04 — Project schedule pressure (compressed timeline) | Medium | Medium

- R-05 — Architectural drawings late (cable measurement bounded) | High | Medium

- R-06 — Brand substitution (customer rejects Siemens) | Low | Medium

- R-07 — After-hours work mandated (~25% premium) | Low | Medium

- R-08 — EE drawing set incomplete (full EE-01..24 missing) | Medium | Low

- R-09 — Casino IAQ regulator demands more sensors | Medium | Low

- R-10 — Hot-cutover required (treats as rehab) | Low | High

### Recent decisions worth revisiting

Decisions made during proposal generation. Review whether each is still right given any new customer answers or drawings received since the decision was made.

- D-001 — Specialized subagents not installed; fallback to general-purpose

- D-002 — Stage classification: Greenfield, despite “Rehabilitation” cover-letter wording

- D-003 — Customer-KB Megaworld brand list is STUB

## 5. Open assumptions to refine

0 assumptions in ‘Open’ status (out of 0 total). Each one is something the proposal currently treats as a known quantity but isn’t actually confirmed. The team should pair each open assumption with the corresponding Q-NNN and chase the customer’s answer.

## 6. Process improvements queued

Items the methodology audit and A/B regression runs flagged for the next playbook pass. These don’t block this proposal but will improve the next one:

- Conduit ratio — currently 30% of total cable length unless overridden. Project-tuned override available via B4-site-factors.yaml (see Op#11).

- Commercial rates — overhead 20% / contingency 7.5% / VAT 12% are defaults. Project-tuned override via 06-commercial-rates.yaml based on risk-register score.

- Cable specs — currently project-blind. Consider authoring A3-cable-spec-rules.yaml per _playbook/sub-routines/build-cable-schedule.md for explicit jurisdiction / brand reasoning.

- MS/TP trunk topology — formula-based fallback; ideally derived from actual A4 panel locations.

## 7. Defensibility check — what’s already strong

Reassurance for the team — items the agent already handled to a defensible standard:

- Every BOQ line traces to a working doc; every working doc cites sources

- Drawing-availability triage committed in writing in 03-doc-inventory.md (per Op#10)

- All assumptions are documented with rationale + impact-if-wrong

- 13-file deliverables package ready for issue with no missing artifacts

- Audit XLSX layer (per Principle F) makes verification work tractable

Generated by _playbook/tools/generate-internal-notes.py. Re-run after any update to the project’s working docs to refresh.