## Summary
A2 — Equipment Takeoff, Audit View
Project | Kingsford Hotel Bacolod — BMS
Canonical source | A2-equipment-takeoff.yaml
How to record corrections | Edit the canonical YAML directly — add a verification: block to the affected row(s)
Totals
Total equipment instances | 23
Equipment classes | 14
Locations | 5
Verification status
Status | Count | % of total
verified | 0 | 0%
needs_correction | 0 | 0%
uncertain | 0 | 0%
unverified | 23 | 100%
⚠ Known weak points
Verify quantities and locations against mechanical / electrical drawings. The 'Make/Model' field is a generic class default — supplier RFQ refines.
How corrections flow
Edit A2-equipment-takeoff.yaml — add a verification: block to the affected row when location or count is confirmed/corrected.

## By Class
Equipment class | Count
Exhaust Fan (General) | 4
AHU (Chilled-Water-Served) | 2
CHW Supply Main Header | 2
Heat Pump | 2
Calorifier (Hot Water Storage Tank) | 2
Precooled Air Handling Unit | 2
Recirculating Pump | 2
Condenser Water Pump | 1
Chiller (Package Water-Cooled) | 1
Primary CHW Pump | 1
Cooling Tower | 1
DOAS Unit | 1
Steam Boiler | 1
Ozone Generator (UV-light or Corona) | 1
TOTAL | 23

## By Location
Location | Count
2F | 9
RD | 7
LG | 5
GF | 1
3F | 1

## Detail
ID | Class | Location | Panel | Primary C/O | Status | Verified by | Date | Drawing ref | Notes
AHU-2/B.2/B.3/PP/CL/FRE/FRD | AHU (Chilled-Water-Served) | 2F | BMS-PNL-BOHAHU-2F | BMS Contractor | unverified
AHU-RD (with CHW mod valve) | AHU (Chilled-Water-Served) | RD | BMS-PNL-AHU-RD | BMS Contractor | unverified
CDWP-1 to CDWP-3 | Condenser Water Pump | 2F | BMS-PNL-CHWPLANT-2F | ME Contractor | unverified
CH-1 to CH-3 | Chiller (Package Water-Cooled) | 2F | BMS-PNL-CHWPLANT-2F | ME Contractor | unverified
CHW Supply & Return Main Header | CHW Supply Main Header | 2F | BMS-PNL-CHWPLANT-2F | BMS Contractor | unverified
CHWP-1 to CHWP-3 | Primary CHW Pump | 2F | BMS-PNL-CHWPLANT-2F | ME Contractor | unverified
CT-1 to CT-3 | Cooling Tower | RD | BMS-PNL-CT-RD | BMS Contractor | unverified
DOAS (Casino) — 2 units | DOAS Unit | 2F | BMS-PNL-CASINO-2F | BMS Contractor | unverified
EF-RD.1/RD.2, EF-1 | Exhaust Fan (General) | RD | BMS-PNL-VENT-RD | ME Contractor | unverified
HP-HZ (×3) | Heat Pump | RD | BMS-PNL-PLUMBING-RD | Equipment Supplier | unverified
HP-LZ (×3) | Heat Pump | LG | BMS-PNL-PLUMBING-LG | Equipment Supplier | unverified
HW Supply & Return Header (LG) | CHW Supply Main Header | LG | BMS-PNL-PLUMBING-LG | BMS Contractor | unverified
HWT-HZ (×3) | Calorifier (Hot Water Storage Tank) | RD | BMS-PNL-PLUMBING-RD | BMS Contractor | unverified
HWT-LZ (×3) | Calorifier (Hot Water Storage Tank) | LG | BMS-PNL-PLUMBING-LG | BMS Contractor | unverified
PAHU-0.1 | Precooled Air Handling Unit | 2F | BMS-PNL-AHU-2F | BMS Contractor | unverified
PAHU-RD (×2) | Precooled Air Handling Unit | RD | BMS-PNL-AHU-RD | ME Contractor | unverified
RP-HZ (×3) | Recirculating Pump | RD | BMS-PNL-PLUMBING-RD | ME Contractor | unverified
RP-LZ (×3) | Recirculating Pump | LG | BMS-PNL-PLUMBING-LG | ME Contractor | unverified
SB-1 & SB-2 | Steam Boiler | LG | BMS-PNL-BOILER-LG | ME Contractor | unverified
Sanitizer for AHU-2M.1/2M.2 | Ozone Generator (UV-light or Corona) | 2F | BMS-PNL-CASINO-2F | Equipment Supplier | unverified
TEF-1.1 to 1.4 + EF-1.2A/LPG.1/1MR.1/1STO.1/MRF.1 | Exhaust Fan (General) | GF | BMS-PNL-VENT-GF | ME Contractor | unverified
TEF-2.1/2.3/2B.3 + EF-2B.1/2B.2/GS.1&GS.2 + EF-2.1 to 2.4 + EF-CHRx2 | Exhaust Fan (General) | 2F | BMS-PNL-VENT-2F | ME Contractor | unverified
TEF-3Ax2/3B/3Cx2/3Dx20 + others | Exhaust Fan (General) | 3F | BMS-PNL-VENT-3F | ME Contractor | unverified

## Verification schema
How to record verification / corrections in A2-equipment-takeoff.yaml
Find the affected row in the YAML by ID (Detail sheet column A) and add a verification: block:
- id: AHU-01
verification: # ADDED by team
status: needs_correction # unverified ¦ verified ¦ needs_correction ¦ uncertain
corrected_location: 3rd Floor Mech Room # team's measured / confirmed value
verified_by: J. Cruz
verified_date: 2026-05-10
drawing_ref: "EE-09 grid B-2"
notes: ""
After saving, re-run: python3 _playbook/tools/generate-deliverables.py <project>
Corrections propagate to B4 manhours, BOQ, and final deliverables automatically.
Recommended verification methods (priority order):
1. Site walkthrough with measurement (most accurate; for cable lengths, after structural completion).
2. Properly-scaled architectural drawings.
3. Mechanical contractor's tray layout combined with BMS panel locations.
4. A-001 default with ±20% contingency in BOQ — last resort.