Table of Contents

# Internal Team Notes — 2026-04-kingsford-bms-AB5

Audience: the proposal team running the next pass on this project.

This document compiles actionable items pulled from the project’s working artifacts. Each section is what to do next — verify, refine, or reconsider — to improve the proposal before it goes to the customer or as part of an RFQ-response cycle.

Sources compiled:

- 07-assumptions.md — assumptions to verify or refine

- 08-customer-clarifications.md — questions to send the customer

- 99-decision-log.md — decisions worth revisiting

- 03-doc-inventory.md — gap analysis on customer inputs

- 05-working-docs/A3-cable-schedule.yaml — cable-length fallbacks to verify

- 05-working-docs/D3-risk-register.md — project risks (if present)

- 09-rfq-package/ — RFQ packages (cost-reduction via competitive bidding)

## 1. Customer clarifications (RFI list)

15 open questions to send the customer. Each has a documented default assumption with cost / scope impact. Resolving these is the highest-leverage path to refining the proposal — every answered Q-NNN may flip an open assumption from Assumed to Confirmed and reduce contingency.

| ID | Question | Default assumed | What an answer changes |
| --- | --- | --- | --- |
| Q-001 | High | Confirm whether per-guestroom HVAC controls (FCU thermostats | Project-specific BMS Points list shows no guestroom FCU poin |
| Q-002 | High | Provide the latest mechanical (HVAC) layout drawings — chill | Drives equipment-placement assumptions, cable runs, panel-to |
| Q-003 | High | Provide required completion date / project schedule. | Drives mobilization, manpower-loading, T&C window, possible |
| Q-004 | Medium | Provide architectural floor plans (all floors). | For accurate cable route lengths and equipment placement. |
| Q-005 | Medium | Provide EE-24 Power Riser Diagram Part 2 of 2. | Confirms guestroom-tower distribution and metering scope. |
| Q-006 | Medium | Provide plumbing/sanitary layouts. | Confirms calorifier, heat-pump, recirc-pump locations. |
| Q-007 | Medium | Confirm BMS network topology and head-end location: isolated | A5/A6 head-end + network architecture. |
| Q-008 | Medium | Confirm approved brand list for: BMS controllers/DDC, superv | Brand-locking affects pricing ±5–15%. |
| Q-009 | Low | Confirm whether hotel PMS integration (per-room occupancy → | If required, gateway + custom point mapping needed. |
| Q-010 | Medium | Confirm casino-zone special points: vault-door status, count | Casino-specific points beyond what’s in BMS-02. |
| Q-011 | Low | Confirm BOH kitchen exhaust / Ansul / hood-fire-suppression | Determines whether BMS-side wiring of fire interlock relays |
| Q-012 | Medium | Confirm commercial terms: warranty period, payment milestone | Commercial-contingency calibration. |
| Q-013 | Low | Confirm working-hours / site-access constraints (after-hours | Labor premium calibration. |
| Q-014 | Low | Confirm training and O&M scope: number of training rounds, a | Discrete priced line items. |
| Q-015 | High | Cover letter says “Rehabilitation” but Construction Bulletin | Highest-leverage classification axis; ±25–30% cost. |

## 2. Verification action items (against drawings, on site, with vendors)

### Cable lengths — fallback rows to verify

Cables tagged legacy_fallback, typical_range:*, or fallback_a001 use agent-reasoned typical-range estimates rather than direct drawing measurements. These are the audit-XLSX rows the team should prioritize when the next set of drawings lands or when site walkthroughs become possible.

| Method tag | Count | Sample row ID |
| --- | --- | --- |
| measured | 19 | (verified) |
| typical_range:bms_panel_power_feed | 13 | P0032 |
| typical_range:plant_room_same_room | 7 | C0001 |
| typical_range:guestroom_corridor | 3 | C0027 |
| typical_range:casino_floor_field | 1 | C0026 |
| unknown | 1 | T0030 |

Open 13-A3-cable-schedule-AUDIT.xlsx to filter and prioritize.

### Other verification items

- Equipment counts — verify against mechanical floor plans where the agent inferred quantities (see open assumptions where Status: Open and category contains ‘count’).

- Panel locations — confirm against architectural drawings and walk the building if accessible.

- Drawing scale calibrations — if any A-NNN entries record drawing-scale calibration assumptions (e.g., grid-bay calibration), spot-check against a second known dimension before the proposal goes out.

- Vendor specifications — for every Equipment Supplier C/O cable / interface, confirm that the supplier’s panel architecture matches the assumed BMS-side interface (HLI vs. hardwired DI/DO).

## 3. Cost-reduction opportunities

### RFQ packages — competitive bidding

The agent prepared 12 RFQ packages categorized by supplier type. Issuing all of them and comparing 3+ quotes per package is the standard cost-reduction lever. Especially impactful for high-value categories:

- bms-controllers-and-panels — typically 5–15% savings vs. catalog pricing on competitive bid

- field-sensors-hvac — typically 5–15% savings vs. catalog pricing on competitive bid

- head-end-servers-workstations — typically 5–15% savings vs. catalog pricing on competitive bid

- network-active — typically 5–15% savings vs. catalog pricing on competitive bid

- power-meters — typically 5–15% savings vs. catalog pricing on competitive bid

- valves-actuators — typically 5–15% savings vs. catalog pricing on competitive bid

Full list in 09-rfq-package/. Send these as soon as the proposal’s commercial side is firm — supplier turnaround is typically 2–4 weeks.

### Other cost levers

- Cable specifications — confirm with the customer whether the assumed jacket rating (e.g., FRLS) is mandated or whether a less-specified cable is acceptable in non-occupied spaces. Material cost difference can be 10–20% on cabling.

- Spare-conductor strategy — current strategy provides 15–25% spares per I/O class. If the customer is willing to accept lower spare margins (commit to the I/O list as-final), cable size drops and material cost reduces 5–10%.

- Make/model consolidation — RFQ packages currently call for spec-level equivalent items. If the customer accepts a single-vendor list (one controller brand, one valve brand), the team can negotiate volume discounts. Document any such consolidation in a new Q-NNN.

- Owner-furnished items — review C1 contractor/owner matrix; items currently assigned to BMS scope that the owner could supply directly (e.g., off-the-shelf workstations, network switches if customer has IT preferences) reduce BMS material markup.

## 4. Risks and decisions to revisit

### Risk register highlights

Open risks from D3-risk-register.md worth re-evaluating before issue:

- R-01 — Q-001 returns “guestroom controls in scope” — adds 2,000–4,000 points + per-room FCU controllers

- R-02 — Q-015 returns “rehabilitation” — adds demolition + after-hours + cable-reuse evaluation | Low |

- R-03 — HVAC layouts (Q-002) reveal AHU/DOAS in dispersed zones, not concentrated 2F | Med | Med

- R-04 — Schedule compression (Q-003 returns <10 weeks) | Low | Med

- R-05 — Brand-list (Q-008) returns non-Siemens preferred for BMS | Low | Low

- R-06 — Casino regulatory (Q-010) requires extra IAQ / vault / count-room points | Low | Med

- R-07 — Customer LAN integration (Q-007) constrains BMS LAN topology | Med | Low

- R-08 — Long-lead equipment (chillers / DOAS) delivery slips | Med | Med

- R-09 — Cable-route fallback (typical-range estimates) inaccurate after final architectural plans | Med

- R-10 — Construction Bulletin No.9 issues new revisions during proposal review | Med | Low

## 5. Open assumptions to refine

0 assumptions in ‘Open’ status (out of 0 total). Each one is something the proposal currently treats as a known quantity but isn’t actually confirmed. The team should pair each open assumption with the corresponding Q-NNN and chase the customer’s answer.

## 6. Process improvements queued

Items the methodology audit and A/B regression runs flagged for the next playbook pass. These don’t block this proposal but will improve the next one:

- Conduit ratio — currently 30% of total cable length unless overridden. Project-tuned override available via B4-site-factors.yaml (see Op#11).

- Commercial rates — overhead 20% / contingency 7.5% / VAT 12% are defaults. Project-tuned override via 06-commercial-rates.yaml based on risk-register score.

- Cable specs — currently project-blind. Consider authoring A3-cable-spec-rules.yaml per _playbook/sub-routines/build-cable-schedule.md for explicit jurisdiction / brand reasoning.

- MS/TP trunk topology — formula-based fallback; ideally derived from actual A4 panel locations.

## 7. Defensibility check — what’s already strong

Reassurance for the team — items the agent already handled to a defensible standard:

- Every BOQ line traces to a working doc; every working doc cites sources

- Drawing-availability triage committed in writing in 03-doc-inventory.md (per Op#10)

- All assumptions are documented with rationale + impact-if-wrong

- 13-file deliverables package ready for issue with no missing artifacts

- Audit XLSX layer (per Principle F) makes verification work tractable

Generated by _playbook/tools/generate-internal-notes.py. Re-run after any update to the project’s working docs to refresh.